## Project Data
Project Name | AI-Assisted Legacy Migration Knowledge Base
Online team meeting | https://fau.zoom-x.de/j/68356420940?pwd=yD6DYSba2jI1DTVMOvI3JmRchu9TuY.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ws01-legacy-migrator
GitHub feature board | https://github.com/orgs/amosproj/projects/109
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/113/views/1
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ws01-legacy-migrator/blob/main/Deliverables/sprint-01/team-logo-blackTshirt.png
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ws01-legacy-migrator/blob/main/Deliverables/sprint-01/team-logo-whiteTshirt.png
Additional materials | ...
Team maling list | oss-amos-proj1@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Fritz | Josefina | https://github.com/Josefinafr | josefina.fritz@fau.de
Barriga Vasquez | Fernando | https://github.com/fbarquez | f.barriga.vasquez@campus.tu-berlin.de
Sternberg | Fiona | https://github.com/Faoilthiama | fiona.sternberg@fau.de
Afzal Yousuf | Ali | https://github.com/3liAf | ali.yousuf@fau.de
Pohlitz | Paul | https://github.com/ppohlitze | p.pohlitz@campus.tu-berlin.de
Rubins | Adrians | https://github.com/AdriansRubins | il4707fu@zedat.fu-berlin.de
Kiesel | Paul | https://github.com/nudelisidle | paul.kiesel@fau.de
Ahm | Raihan | https://github.com/RaihanFAU | ahm.raihan@fau.de
Marques | Rafael | https://github.com/RafaelMcMarques | rafael.mc.marques@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-10-14 | Fernando | Josefina | Everyone else | N/A | Fiona
2 | 2026-10-21 | Josefina | Fernando | Everyone else | Ali | Fiona
3 | 2026-10-28 | Fernando | Josefina | Everyone else | Paul K. | Fiona
4 | 2026-11-04 | Josefina | Fernando | Everyone else | Adrians | Fiona
5 | 2026-11-11 | Fernando | Josefina | Everyone else | Paul P. | Fiona
6 | 2026-11-18 | Josefina | Fernando | Everyone else | Raihan | Fiona
7 | 2026-11-25 | Fernando | Josefina | Everyone else | Rafael | Fiona | Mid-term due
8 | 2026-12-02 | Josefina | Fernando | Everyone else | Ali | Fiona
9 | 2026-12-09 | Fernando | Josefina | Everyone else | Paul K. | Fiona
10 | 2027-01-11 | Josefina | Fernando | Everyone else | Adrians | Fiona
11 | 2027-01-18 | Fernando | Josefina | Everyone else | Paul P. | Fiona
12 | 2027-01-25 | Josefina | Fernando | Everyone else | Raihan | Fiona
13 | 2027-02-01 | Fernando | Josefina | Everyone else | Rafael | Fiona
14 | 2027-02-08 | Josefina | Fernando | Everyone else | Ali | Fiona | Demo day!
15 | 2027-02-15 | Fernando | Josefina | Everyone else | Paul K. | Fiona | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals
- Develop a useable and useful Prototype - Prototype should be compatible with MIT Software Licenses - Meet Requirements (that we don’t know yet) from our industry partner - A good Teamwork - A Demo Version of the Prototype on Demo-day - Keep the Project realistic - Prototype should be easily demonstratable on Demo-day - Preferably locally testable (Ollama)
Meeting norms
- Meetings will be held in English - Be on time and come prepared > Punishments - Camera should be turned on (If it goes) - Let everyone speak and respect opinions and boundaries - If you are sick write a quick chat on WhatsApp and write the Professor
Working norms
- Ask for help if needed / Be helpful to others - Are you sick or unable to end your sprint work please let the POs know - AI Assistant Coding: Developer self should Review it first and the make a pull request - if AI used for git commit messages: PROPERLY Double check and remove "co-authored by Claude / etc." - Suggestion from Dirk Riehle: Required Review (If you create a merge request, you must review at least one another merge request) - When AI Agents are used: Create a system prompt file (for example .Vscode/copilot-instructions.md for GitHub-Copilot ) and write down our coding norms there so that the AI adheres to them - Main Branch just touchable by the Release Manager that week – by Pull Request from Dev Branch - Dev branches with split branches (Title of backlog) – Pull request needs to be review - Breaking Change/Bugs handled by Release Manager and the one who caused it - Dirk Riehle said that collaborative coding must be annotated with a "Co-authored-by: Firstname Lastname <uni-email@uni.de>" at the end of a git commit message, one line per coworker. "Assigned to ..." flags on GitHub Projects work items will probably not be graded - Ensure local, easy reproducability and testability during development, right from the start. This is done by writing setup and start scripts, where it is necessary (instead of executing a module with long config files and 2329 env variables) - We all push into the develop branch then the release manager merges this then with the main branch
Coordination norms
- Planning Board Coordination - If you disagree about smth - discuss it with each other first via Discord/WA and maybe bring it with you to the team meeting session - Never move feature to "Feature Archive" (Finished) column without a review in "Awaiting Review" column first - When you assign someone else to a feature, notify them explicitly WhatsApp
Communication norms
- We set up a Discord Server - WhatsApp as main Communication Form - Happy Go Lucky: for twice a week Standup Email SDs (weekly for POs, SM) - Email with Wolfgang run by Fernando and Josefina - Feel free to text privately on WhatsApp if stuff comes up
Consideration norms
- Be patient – language differences, not same level of programming exp - respect each other’s time - Be nice and kind to each other - Be open to constructive feedback and focus on solving problems rather than blaming each other - In planning poker always considere your peers thez might not have the same knowledge as you have
Cont. improvement norms
- No automating push into main and dev branch - Feature branch are named after tickets - After issue is resolved the feature branch for the ticket won’t be deleted - Merge requests shall not be reviewed automatically - Everybody gets informed about resolved pull requests -Maybe leave a message on WA - If there is any issue that has to be resolved immediately find a time to talk together on Discord - Build process create a useful artefact - Artefacts are stored on Github - Vertical slices workstream
Rewards
- Get a T-shirt - Get a good grade - Online Celebration - Small Celebration for every release - A good Linkdin Profil : “What AMOS project taught me about B2B SAAS this week”
Sanctions
- If you’re late to a team meeting, you have to dance when you join. - If you have to complete a penalty, you can choose to dance or sing. - https://allkaraoke.party/game/?playlist=English&song=radiohead-creep
Signatures
Scrum Master | Fiona
Product owner | Fernando
Product owner | Josefina
Software developer | Paul
Software developer | Ali
Software developer | Adrian
Software developer | Rafael
Software developer | Raihan
Software developer | Paul

## Product Goal
Product Vision | Project Mission
Enable software teams to migrate legacy systems with confidence by providing a persistent, connected knowledge base of legacy code, target code, domain knowledge and system dependencies. Through natural-language queries and up-to-date architecture views, teams can understand migration progress, preserve essential knowledge and make informed decisions about what to migrate or decommission next. | Develop and validate a prototype during the AMOS semester using a shareable reference project with a realistic migration history. Evaluate existing analysis tools, connect relevant information in a knowledge graph and demonstrate reliable natural-language answers about at least one migration step. Agree on measurable success criteria with the industry partner and define the scope of generated architecture views.

## Product Glossary
Term | Definition
Legacy System | The existing software system whose functionality is gradually migrated to a new system. Some components remain active during the transition.
Target System | The new system that gradually replaces legacy functionality. Its actual code is analysed to distinguish implemented functionality from planned work.
Knowledge Base | A persistent, versioned collection of connected information about legacy code, target code, domain knowledge and migration dependencies.
Knowledge Graph | A representation of information as nodes and relationships, connecting elements such as code components, bounded contexts and dependencies.
Abstract Syntax Tree (AST) | A structured representation of source code used to analyse elements such as classes, methods and fields.
Domain Model | A structured description of the business domain, including bounded contexts, business terminology, rules and events.
Bounded Context | A defined business boundary within which a particular domain model and its terminology apply. It can be linked to its implementations in both systems.
Ubiquitous Language | The shared business vocabulary used by domain experts and developers within a bounded context.
Coupling | A dependency between components or systems, such as direct calls, shared database tables or messaging routes. Remaining coupling can affect decommissioning decisions.
Decommissioning | Taking a legacy component out of operation after its functionality and remaining dependencies have been addressed.
Strangler Fig Migration | An incremental migration approach in which a new system gradually replaces the legacy system through parallel operation, completion and decommissioning.
Deterministic Ingestion | The stage that extracts and stores structural facts, such as code relationships and deployment information, without using an LLM.
LLM-Based Comprehension | The stage in which a large language model generates summaries and explanations from ingested information and stores them in the knowledge base.
Retrieval-Augmented Generation (RAG) | An approach that retrieves relevant knowledge-base information to support an LLM’s answer to a user’s question.
arc42 | An architecture documentation framework. The project specifically targets its context, building block and deployment views.
Context View | An architecture view showing the system boundary, external actors, neighbouring systems and their interfaces.
Building Block View | An architecture view showing the static structure of components, services or modules. In this project, it shows legacy and target elements together with their status.
Deployment View | An architecture view showing where components run and how they connect through infrastructure such as databases and messaging systems.
Synthetic Reference System | A shareable example system with realistic migration scenarios, used to develop and validate the prototype without confidential client code or data.
Migration Step | A defined stage in the reference system’s migration history. Comparing consecutive steps reveals changes to code, deployments and dependencies.
Minimum Viable Product (MVP) | The initial prototype scope agreed with the industry partner. The kickoff discussion identifies answering natural-language questions about at least one migration step as the minimum goal.

## Sprint Goals
Sprint # | Sprint goal
1 | United Understanding
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# |  | Context | Name | Version | Licence (SPDX) | Comment
# | Component | Type | Component | Version | Supplier | Notes
1 | python | container | python | 3.12 | Python Software Foundation | Base image for pipeline and MCP server; code-review-graph needs Python >= 3.10
2 | git | application | git | unpinned (resolve at first lockfile) | Git project | Host/base-image tool for git worktree checkouts; invoked as a separate process, not linked or modified
3 | code-review-graph | library | code-review-graph | 2.3.9 | Tirth (tirth8205) | Primary structural extractor (PyPI release 18 Sep 2026)
4 | sqlglot | library | sqlglot | 30.22.0 | Toby Mao and contributors | SQL read/write extraction (release 9 Oct 2026)
5 | atlassian-python-api | library | atlassian-python-api | 5.0.5 | atlassian-api community (not Atlassian) | Jira and Confluence connectors (Cloud and Server/DC); licence V, version from docs (S)
6 | markdown-it-py | library | markdown-it-py | unpinned (resolve at first lockfile) | Executable Books | Markdown parsing (headings, links, code spans)
7 | markdownify | library | markdownify | unpinned (resolve at first lockfile) | Matthew Tretter and contributors | Confluence storage format (XHTML) to markdown
8 | mcp | library | mcp | unpinned (resolve at first lockfile) | Model Context Protocol project | MCP tool server SDK
9 | pydantic | library | pydantic | unpinned (resolve at first lockfile) | Pydantic Services Inc. and contributors | Canonical fact schema and validation
10 | ollama (Python client) | library | ollama (Python client) | unpinned (resolve at first lockfile) | Ollama Inc. | Chat and embedding calls to the local model runtime
11 | repowise | library | repowise | 0.58.0 | repowise-dev | Second extractor: workspaces and cross-repo contracts. Disable telemetry (opt-out). Version observed on PyPI earlier in the survey
12 | neo4j (Python driver) | library | neo4j (Python driver) | unpinned (resolve at first lockfile) | Neo4j Inc. | Loader and MCP queries
13 | PyDriller | library | PyDriller | unpinned (resolve at first lockfile) | Davide Spadini and contributors | Git history mining (commits, changed files, issue keys)
14 | ollama | container | ollama | 0.40.9 | Ollama Inc. | Local LLM runtime. Sources disagree on latest (0.40.5 / 0.40.9 / 0.40.10); pinned 0.40.9. Cloud features must be disabled (offline configuration)
15 | LibreChat | container | LibreChat | 0.8.8 | LibreChat (Danny Avila and contributors) | Chat UI (release 1 Oct 2026). Verify compose services at lock time
16 | FerretDB | container | FerretDB | 2.x (unpinned (resolve at first lockfile)) | FerretDB Inc. | Replaces MongoDB (SSPL) as LibreChat's document store
17 | DocumentDB PostgreSQL extension | library | DocumentDB PostgreSQL extension | unpinned (resolve at first lockfile) | Microsoft | Backend required by FerretDB 2.x; licence to verify
18 | PostgreSQL | container | PostgreSQL | 17 (minor unpinned (resolve at first lockfile)) | PostgreSQL Global Development Group | Backend for FerretDB (both visions); in Vision A also graph + vector store
19 | Neo4j Community Edition | container | Neo4j Community Edition | calendar version unpinned (resolve at first lockfile) | Neo4j Inc. | Graph store and vector index; run unmodified as a separate server
20 | code-maat | application | code-maat | unpinned (resolve at first lockfile) | Adam Tornhill | Co-change coupling, run as a separate JVM process; optional input
21 | gpt-oss-20b | machine-learning-model | gpt-oss-20b | revision unpinned (resolve at first lockfile) | OpenAI | Chat model; Apache-2.0 plus the gpt-oss usage policy
22 | Qwen3-Embedding-0.6B | machine-learning-model | Qwen3-Embedding-0.6B | revision unpinned (resolve at first lockfile) | Qwen team, Alibaba Cloud | Embedding model; check licence on the model card (Qwen licences differ per checkpoint)
23 | pytest | library | pytest | unpinned (resolve at first lockfile) | pytest-dev | Dev-only: tests (DoD)
24 | cyclonedx-bom (cyclonedx-py) | application | cyclonedx-bom (cyclonedx-py) | unpinned (resolve at first lockfile) | OWASP CycloneDX | Dev-only: generates the build SBOM from the lockfile
25 | syft | application | syft | unpinned (resolve at first lockfile) | Anchore | Dev-only: SBOM for container images
26 | pip-licenses | application | pip-licenses | unpinned (resolve at first lockfile) | raimon49 | Dev-only: licence gate in CI
27 | MongoDB Community | container | MongoDB Community | - | MongoDB Inc. | Default LibreChat store; excluded (non-OSI), replaced by FerretDB
28 | Meilisearch | container | Meilisearch | - | Meili SAS | Optional LibreChat search; disabled

## (Draft) Bill of Materials
# | Context | Name | Version | Licence (SPDX) | Comment
1 | container | python | 3.12 | PSF-2.0 | Base image for pipeline and MCP server; code-review-graph needs Python >= 3.10
2 | application | git | unpinned (resolve at first lockfile) | GPL-2.0-only | Host/base-image tool for git worktree checkouts; invoked as a separate process, not linked or modified
3 | library | code-review-graph | 2.3.9 | MIT | Primary structural extractor (PyPI release 18 Sep 2026)
4 | library | sqlglot | 30.22.0 | MIT | SQL read/write extraction (release 9 Oct 2026)
5 | library | atlassian-python-api | 5.0.5 | Apache-2.0 | Jira and Confluence connectors (Cloud and Server/DC); licence V, version from docs (S)
6 | library | markdown-it-py | unpinned (resolve at first lockfile) | MIT | Markdown parsing (headings, links, code spans)
7 | library | markdownify | unpinned (resolve at first lockfile) | MIT | Confluence storage format (XHTML) to markdown
8 | library | mcp | unpinned (resolve at first lockfile) | MIT | MCP tool server SDK
9 | library | pydantic | unpinned (resolve at first lockfile) | MIT | Canonical fact schema and validation
10 | library | ollama (Python client) | unpinned (resolve at first lockfile) | MIT | Chat and embedding calls to the local model runtime
11 | library | asyncpg | unpinned (resolve at first lockfile) | Apache-2.0 | PostgreSQL driver; chosen instead of psycopg (LGPL-3.0) to keep Vision A permissive. AGE is queried via SQL cypher() calls, not the psycopg-based AGE driver
12 | container | ollama | 0.40.9 | MIT | Local LLM runtime. Sources disagree on latest (0.40.5 / 0.40.9 / 0.40.10); pinned 0.40.9. Cloud features must be disabled (offline configuration)
13 | container | LibreChat | 0.8.8 | MIT | Chat UI (release 1 Oct 2026). Verify compose services at lock time
14 | container | FerretDB | 2.x (unpinned (resolve at first lockfile)) | Apache-2.0 | Replaces MongoDB (SSPL) as LibreChat's document store
15 | library | DocumentDB PostgreSQL extension | unpinned (resolve at first lockfile) | MIT | Backend required by FerretDB 2.x; licence to verify
16 | container | PostgreSQL | 17 (minor unpinned (resolve at first lockfile)) | PostgreSQL | Backend for FerretDB (both visions); in Vision A also graph + vector store
17 | library | Apache AGE | 1.7.0 (PG17) | Apache-2.0 | Graph extension (openCypher) for PostgreSQL 17
18 | library | pgvector | unpinned (resolve at first lockfile) | PostgreSQL | Vector index in PostgreSQL
19 | machine-learning-model | gpt-oss-20b | revision unpinned (resolve at first lockfile) | Apache-2.0 | Chat model; Apache-2.0 plus the gpt-oss usage policy
20 | machine-learning-model | Qwen3-Embedding-0.6B | revision unpinned (resolve at first lockfile) | Apache-2.0 | Embedding model; check licence on the model card (Qwen licences differ per checkpoint)
21 | library | pytest | unpinned (resolve at first lockfile) | MIT | Dev-only: tests (DoD)
22 | application | cyclonedx-bom (cyclonedx-py) | unpinned (resolve at first lockfile) | Apache-2.0 | Dev-only: generates the build SBOM from the lockfile
23 | application | syft | unpinned (resolve at first lockfile) | Apache-2.0 | Dev-only: SBOM for container images
24 | application | pip-licenses | unpinned (resolve at first lockfile) | MIT | Dev-only: licence gate in CI
25 | container | MongoDB Community | - | SSPL-1.0 | Default LibreChat store; excluded (non-OSI), replaced by FerretDB
26 | container | Meilisearch | - | MIT | Optional LibreChat search; disabled

## Planning Poker
Last Name | First Name | Value
Fritz | Josefina | 0 | 4.6667 | NOK
Barriga Vasquez | Fernando | 0
Sternberg | Fiona
Afzal Yousuf | Ali | 5
Pohlitz | Paul | 5 | 0 | No size
Rubins | Adrians | 5 | 1 | Trivial size
Kiesel | Paul | 5 | 2 | Small size
Ahm | Raihan | 5 | 3 | Medium size
Marques | Rafael | 3 | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value